## Capital Cost Estimate
Detailed Reclamation and Closure/Closeout Bond Cost Estimate - Capital Costs
Fort Knox Mine Reclamation Plan
|  | Tasks |  |  | Fort Knox Mine Reclamation Plan April 2001 | [7 empty] | CSP2 2003 Estimate - Scenario 1 |  |  |  | CSP2 2003 Estimate - Scenario 2 |  |  |  | CSP2 2003 Estimate - Scenario 3 |  |  |  | CSP2 2003 Estimate - Scenario 4
Line |  |  |  |  | Labor | Equipment | Materials | Total Cost | Unit | No. Units | Unit Cost | Total Cost | Unit | No. Units | Unit Cost | Total Cost | Unit | No. Units | Unit Cost | Total Cost | Unit | No. Units | Unit Cost | Total Cost | Unit | No. Units | Unit Cost | Total Cost
1 | Mine Waste Pile Reclamation
1a | Yellow Pup Dump
Flat
1a1 |  |  | Contour |  | 24462.225 | 60018 |  | 84480.225 | ac | 80 | 1056.0028 | 84480.225 | ac | 80 | 1056.0028 | 84480.225 | ac | 80 | 1584.0042 | 126720.3375 | ac | 80 | 1584.0042 | 126720.3375 | ac | 80 | 1584.0042 | 126720.3375
1a2 |  |  | Rip
1a3 |  |  | Cover
1a4 |  |  | Growth Medium
Sloped
1a5 |  |  | Contour |  | 12212.775 | 65890 |  | 78102.775 | ac | 40 | 1952.5694 | 78102.775 | ac | 40 | 1952.5694 | 78102.775 | ac | 40 | 2928.8541 | 117154.1625 | ac | 40 | 2928.8541 | 117154.1625 | ac | 40 | 2928.8541 | 117154.1625
1a6 |  |  | Rip
1a7 |  |  | Cover
1a8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 36675 | 125908 | 0 | 162583 | ac | 120 | 1354.8583 | 162583 | ac | 120 | 1354.8583 | 162583 | ac | 120 | 2032.2875 | 243874.5 | ac | 120 | 2032.2875 | 243874.5 | ac | 120 | 2032.2875 | 243874.5
Flat
1a9 |  |  | Blade
1a10 |  |  | Seeding (seed, equipment, labor) |  |  | 4290 | 8874.9819 | 13164.9819 | ac | 80 | 164.5623 | 13164.9819 | ac | 80 | 164.5623 | 13164.9819 | ac | 80 | 1500 | 120000 | ac | 80 | 1500 | 120000 | ac | 80 | 1500 | 120000
Sloped
1a11 |  |  | Blade
1a12 |  |  | Seeding (seed + equipment + labor) |  |  | 2306 | 4430.8381 | 6736.8381 | ac | 40 | 168.421 | 6736.8381 | ac | 40 | 168.421 | 6736.8381 | ac | 40 | 2500 | 100000 | ac | 40 | 2500 | 100000 | ac | 40 | 2500 | 100000
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 6596 | 13305.82 | 19901.82 | ac | 120 | 165.8485 | 19901.82 | ac | 120 | 165.8485 | 19901.82 | ac | 120 | 1833.3333 | 220000 | ac | 120 | 1833.3333 | 220000 | ac | 120 | 1833.3333 | 220000
| Yellow Pup Dump Subtotal |  |  |  | 36675 | 132504 | 13305.82 | 182484.82 | ac | 120 | 1520.7068 | 182484.82 | ac | 120 | 1520.7068 | 182484.82 | ac | 120 | 3865.6208 | 463874.5 | ac | 120 | 3865.6208 | 463874.5 | ac | 120 | 3865.6208 | 463874.5
1b | Barnes Creek Dump
Flat
1b1 |  |  | Contour |  | 48296.568 | 144716.355 |  | 193012.923 | ac | 108.4 | 1780.562 | 193012.923 | ac | 108.4 | 1780.562 | 193012.923 | ac | 108.4 | 2670.843 | 289519.3845 | ac | 108.4 | 2670.843 | 289519.3845 | ac | 108.4 | 2670.843 | 289519.3845
1b2 |  |  | Rip
1b3 |  |  | Cover
1b4 |  |  | Growth Medium
Sloped
1b5 |  |  | Contour |  | 27641.432 | 162407.07 |  | 190048.502 | ac | 62.1 | 3060.3624 | 190048.502 | ac | 62.1 | 3060.3624 | 190048.502 | ac | 62.1 | 4590.5435 | 285072.753 | ac | 62.1 | 4590.5435 | 285072.753 | ac | 62.1 | 4590.5435 | 285072.753
1b6 |  |  | Rip
1b7 |  |  | Cover
1b8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 75938 | 307123.425 | 0 | 383061.425 | ac | 170.5 | 2246.6946 | 383061.425 | ac | 170.5 | 2246.6946 | 383061.425 | ac | 170.5 | 3370.0419 | 574592.1375 | ac | 170.5 | 3370.0419 | 574592.1375 | ac | 170.5 | 3370.0419 | 574592.1375
Flat
1b9 |  |  | Blade
1b10 |  |  | Seeding (seed, equipment, labor) |  |  | 5793.27 | 12011.2925 | 17804.5625 | ac | 108.4 | 164.2487 | 17804.5625 | ac | 108.4 | 164.2487 | 17804.5625 | ac | 108.4 | 1500 | 162600 | ac | 108.4 | 1500 | 162600 | ac | 108.4 | 1500 | 162600
Sloped
1b11 |  |  | Blade
1b12 |  |  | Seeding (seed + equipment + labor) |  |  | 3625.755 | 6874.3875 | 10500.1425 | ac | 62.1 | 169.0844 | 10500.1425 | ac | 62.1 | 169.0844 | 10500.1425 | ac | 62.1 | 2500 | 155250 | ac | 62.1 | 2500 | 155250 | ac | 62.1 | 2500 | 155250
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 9419.025 | 18885.68 | 28304.705 | ac | 341 | 83.005 | 28304.705 | ac | 341 | 83.005 | 28304.705 | ac | 341 | 932.1114 | 317850 | ac | 341 | 932.1114 | 317850 | ac | 341 | 932.1114 | 317850
| Barnes Creek Dump Subtotal |  |  |  | 75938 | 316542.45 | 18885.68 | 411366.13 | ac | 170.5 | 2412.7046 | 411366.13 | ac | 170.5 | 2412.7046 | 411366.13 | ac | 170.5 | 5234.2647 | 892442.1375 | ac | 170.5 | 5234.2647 | 892442.1375 | ac | 170.5 | 5234.2647 | 892442.1375
1c | Lowgrade Stockpile
Flat
1c1 |  |  | Contour |  | 16920.222 | 52176.645 |  | 69096.867 | ac | 38.1 | 1813.5661 | 69096.867 | ac | 38.1 | 1813.5661 | 69096.867 | ac | 38.1 | 2720.3491 | 103645.3005 | ac | 38.1 | 2720.3491 | 103645.3005 | ac | 38.1 | 2720.3491 | 103645.3005
1c2 |  |  | Rip
1c3 |  |  | Cover
1c4 |  |  | Growth Medium
Sloped
1c5 |  |  | Contour |  | 10458.778 | 58554.93 |  | 69013.708 | ac | 23.5 | 2936.7535 | 69013.708 | ac | 23.5 | 2936.7535 | 69013.708 | ac | 23.5 | 4405.1303 | 103520.562 | ac | 23.5 | 4405.1303 | 103520.562 | ac | 23.5 | 4405.1303 | 103520.562
1c6 |  |  | Rip
1c7 |  |  | Cover
1c8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 27379 | 110731.575 | 0 | 138110.575 | ac | 61.6 | 2242.0548 | 138110.575 | ac | 61.6 | 2242.0548 | 138110.575 | ac | 61.6 | 3363.0822 | 207165.8625 | ac | 61.6 | 3363.0822 | 207165.8625 | ac | 61.6 | 3363.0822 | 207165.8625
Flat
1c9 |  |  | Blade
1c10 |  |  | Seeding (seed, equipment, labor) |  |  | 2088.73 | 4220.013 | 6308.743 | ac | 38.1 | 165.5838 | 6308.743 | ac | 38.1 | 165.5838 | 6308.743 | ac | 38.1 | 1500 | 57150 | ac | 38.1 | 1500 | 57150 | ac | 38.1 | 1500 | 57150
Sloped
1c11 |  |  | Blade
1c12 |  |  | Seeding (seed + equipment + labor) |  |  | 1307.245 | 2608.487 | 3915.732 | ac | 23.5 | 166.6269 | 3915.732 | ac | 23.5 | 166.6269 | 3915.732 | ac | 23.5 | 2500 | 58750 | ac | 23.5 | 2500 | 58750 | ac | 23.5 | 2500 | 58750
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 3395.975 | 6828.5 | 10224.475 | ac | 61.6 | 165.9817 | 10224.475 | ac | 61.6 | 165.9817 | 10224.475 | ac | 61.6 | 1881.4935 | 115900 | ac | 61.6 | 1881.4935 | 115900 | ac | 61.6 | 1881.4935 | 115900
| Lowgrade Stockpile Subtotal |  |  |  | 27379 | 114127.55 | 6828.5 | 148335.05 | ac | 61.6 | 2408.0365 | 148335.05 | ac | 61.6 | 2408.0365 | 148335.05 | ac | 61.6 | 5244.5757 | 323065.8625 | ac | 61.6 | 5244.5757 | 323065.8625 | ac | 61.6 | 5244.5757 | 323065.8625
1d | Install additional stormwater controls
1e | Install additional groundwater controls
| Subtotal Waste Rock Area Reclamation |  |  |  | 139992 | 563174 | 39020 | 742186 | ac | 352.1 | 2107.8841 | 742186 | ac | 352.1 | 2107.8841 | 742186 | ac | 352.1 | 4769.618 | 1679382.5 | ac | 352.1 | 4769.618 | 1679382.5 | ac | 352.1 | 4769.618 | 1679382.5
2 | Borrow Area Reclamation
2a | Borrow # 12
Flat
2a1 |  |  | Contour |  | 7995 | 27724.168 |  | 35719.168 | ac | 31 | 1152.2312 | 35719.168 | ac | 31 | 1152.2312 | 35719.168 | ac | 31 | 1728.3468 | 53578.752 | ac | 31 | 1728.3468 | 53578.752 | ac | 31 | 1728.3468 | 53578.752
2a2 |  |  | Rip
2a3 |  |  | Cover
2a4 |  |  | Growth Medium
Sloped
2a5 |  |  | Contour
2a6 |  |  | Rip
2a7 |  |  | Cover
2a8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 7995 | 27724.168 | 0 | 35719.168 | ac | 31 | 1152.2312 | 35719.168 | ac | 31 | 1152.2312 | 35719.168 | ac | 31 | 1728.3468 | 53578.752 | ac | 31 | 1728.3468 | 53578.752 | ac | 31 | 1728.3468 | 53578.752
Flat
2a9 |  |  | Blade
2a10 |  |  | Seeding (seed, equipment, labor) |  |  | 1662.22 | 3343.3175 | 5005.5375 | ac | 31 | 161.469 | 5005.5375 | ac | 31 | 161.469 | 5005.5375 | ac | 31 | 1500 | 46500 | ac | 31 | 1500 | 46500 | ac | 31 | 1500 | 46500
Sloped
2a11 |  |  | Blade
2a12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 1662.22 | 3343.3175 | 5005.5375 | ac | 31 | 161.469 | 5005.5375 | ac | 31 | 161.469 | 5005.5375 | ac | 31 | 1500 | 46500 | ac | 31 | 1500 | 46500 | ac | 31 | 1500 | 46500
| Borrow #12 Subtotal |  |  |  | 7995 | 29386.388 | 3343.3175 | 40724.7055 | ac | 31 | 1313.7002 | 40724.7055 | ac | 31 | 1313.7002 | 40724.7055 | ac | 31 | 3228.3468 | 100078.752 | ac | 31 | 3228.3468 | 100078.752 | ac | 31 | 3228.3468 | 100078.752
2b | Laydown Yard
Flat
2b1 |  |  | Contour |  | 5614 | 17140.775 |  | 22754.775 | ac | 25 | 910.191 | 22754.775 | ac | 25 | 910.191 | 22754.775 | ac | 25 | 1365.2865 | 34132.1625 | ac | 25 | 1365.2865 | 34132.1625 | ac | 25 | 1365.2865 | 34132.1625
2b2 |  |  | Rip
2b3 |  |  | Cover
2b4 |  |  | Growth Medium
Sloped
2b5 |  |  | Contour
2b6 |  |  | Rip
2b7 |  |  | Cover
2b8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 5614 | 17140.775 | 0 | 22754.775 | ac | 25 | 910.191 | 22754.775 | ac | 25 | 910.191 | 22754.775 | ac | 25 | 1365.2865 | 34132.1625 | ac | 25 | 1365.2865 | 34132.1625 | ac | 25 | 1365.2865 | 34132.1625
Flat
2b9 |  |  | Blade
2b10 |  |  | Seeding (seed, equipment, labor) |  |  | 1340.5 | 2696.2238 | 4036.7238 | ac | 25 | 161.469 | 4036.7238 | ac | 25 | 161.469 | 4036.7238 | ac | 25 | 1500 | 37500 | ac | 25 | 1500 | 37500 | ac | 25 | 1500 | 37500
Sloped
2b11 |  |  | Blade
2b12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 1340.5 | 2696.2238 | 4036.7238 | ac | 25 | 161.469 | 4036.7238 | ac | 25 | 161.469 | 4036.7238 | ac | 25 | 1500 | 37500 | ac | 25 | 1500 | 37500 | ac | 25 | 1500 | 37500
| Laydown Yard Subtotal |  |  |  | 5614 | 18481.275 | 2696.2238 | 26791.4988 | ac | 25 | 1071.66 | 26791.4988 | ac | 25 | 1071.66 | 26791.4988 | ac | 25 | 2865.2865 | 71632.1625 | ac | 25 | 2865.2865 | 71632.1625 | ac | 25 | 2865.2865 | 71632.1625
2c | Aggregate Crusher
Flat
2c1 |  |  | Contour |  | 2708 | 9392.103 |  | 12100.103 | ac | 10.5 | 1152.3908 | 12100.103 | ac | 10.5 | 1152.3908 | 12100.103 | ac | 10.5 | 1728.5861 | 18150.1545 | ac | 10.5 | 1728.5861 | 18150.1545 | ac | 10.5 | 1728.5861 | 18150.1545
2c2 |  |  | Rip
2c3 |  |  | Cover
2c4 |  |  | Growth Medium
Sloped
2c5 |  |  | Contour
2c6 |  |  | Rip
2c7 |  |  | Cover
2c8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 2708 | 9392.103 | 0 | 12100.103 | ac | 10.5 | 1152.3908 | 12100.103 | ac | 10.5 | 1152.3908 | 12100.103 | ac | 10.5 | 1728.5861 | 18150.1545 | ac | 10.5 | 1728.5861 | 18150.1545 | ac | 10.5 | 1728.5861 | 18150.1545
Flat
2c9 |  |  | Blade
2c10 |  |  | Seeding (seed, equipment, labor) |  |  | 563.01 | 1132.414 | 1695.424 | ac | 10.5 | 161.469 | 1695.424 | ac | 10.5 | 161.469 | 1695.424 | ac | 10.5 | 1500 | 15750 | ac | 10.5 | 1500 | 15750 | ac | 10.5 | 1500 | 15750
Sloped
2c11 |  |  | Blade
2c12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 563.01 | 1132.414 | 1695.424 | ac | 10.5 | 161.469 | 1695.424 | ac | 10.5 | 161.469 | 1695.424 | ac | 10.5 | 1500 | 15750 | ac | 10.5 | 1500 | 15750 | ac | 10.5 | 1500 | 15750
| Aggregate Crusher Subtotal |  |  |  | 2708 | 9955.113 | 1132.414 | 13795.527 | ac | 10.5 | 1313.8597 | 13795.527 | ac | 10.5 | 1313.8597 | 13795.527 | ac | 10.5 | 3228.5861 | 33900.1545 | ac | 10.5 | 3228.5861 | 33900.1545 | ac | 10.5 | 3228.5861 | 33900.1545
2d | Borrow # 5
Flat
2d1 |  |  | Contour |  | 22664 | 92931.93 |  | 115595.93 | ac | 65 | 1778.3989 | 115595.93 | ac | 65 | 1778.3989 | 115595.93 | ac | 65 | 2667.5984 | 173393.895 | ac | 65 | 2667.5984 | 173393.895 | ac | 65 | 2667.5984 | 173393.895
2d2 |  |  | Rip
2d3 |  |  | Cover
2d4 |  |  | Growth Medium
Sloped
2d5 |  |  | Contour
2d6 |  |  | Rip
2d7 |  |  | Cover
2d8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 22664 | 92931.93 | 0 | 115595.93 | ac | 65 | 1778.3989 | 115595.93 | ac | 65 | 1778.3989 | 115595.93 | ac | 65 | 2667.5984 | 173393.895 | ac | 65 | 2667.5984 | 173393.895 | ac | 65 | 2667.5984 | 173393.895
Flat
2d9 |  |  | Blade
2d10 |  |  | Seeding (seed, equipment, labor) |  |  | 3485.3 | 7010.1818 | 10495.4818 | ac | 65 | 161.469 | 10495.4818 | ac | 65 | 161.469 | 10495.4818 | ac | 65 | 1500 | 97500 | ac | 65 | 1500 | 97500 | ac | 65 | 1500 | 97500
Sloped
2d11 |  |  | Blade
2d12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 3485.3 | 7010.1818 | 10495.4818 | ac | 65 | 161.469 | 10495.4818 | ac | 65 | 161.469 | 10495.4818 | ac | 65 | 1500 | 97500 | ac | 65 | 1500 | 97500 | ac | 65 | 1500 | 97500
| Borrow # 5 Subtotal |  |  |  | 22664 | 96417.23 | 7010.1818 | 126091.4118 | ac | 65 | 1939.8679 | 126091.4118 | ac | 65 | 1939.8679 | 126091.4118 | ac | 65 | 4167.5984 | 270893.895 | ac | 65 | 4167.5984 | 270893.895 | ac | 65 | 4167.5984 | 270893.895
2e | Borrow MB-Pit 1 & Scenic Overlook
Flat
2e1 |  |  | Contour |  | 0 | 0 |  | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 9.5 | 1733 | 16463.5 | ac | 9.5 | 1733 | 16463.5 | ac | 9.5 | 1733 | 16463.5
2e2 |  |  | Rip
2e3 |  |  | Cover
2e4 |  |  | Growth Medium
Sloped
2e5 |  |  | Contour
2e6 |  |  | Rip
2e7 |  |  | Cover
2e8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 9.5 | 1733 | 16463.5 | ac | 9.5 | 1733 | 16463.5 | ac | 9.5 | 1733 | 16463.5
Flat
2e9 |  |  | Blade
2e10 |  |  | Seeding (seed, equipment, labor) |  |  | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 9.5 | 1500 | 14250 | ac | 9.5 | 1500 | 14250 | ac | 9.5 | 1500 | 14250
Sloped
2e11 |  |  | Blade
2e12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 9.5 | 1500 | 14250 | ac | 9.5 | 1500 | 14250 | ac | 9.5 | 1500 | 14250
| Borrow MB-Pit 1 & Scenic Overlook Subtotal |  |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 9.5 | 3233 | 30713.5 | ac | 9.5 | 3233 | 30713.5 | ac | 9.5 | 3233 | 30713.5
2f | Borrow MB-Pit 2
|  | Flat |  |  | 0
2f1 |  |  | Contour |  |  | 0 |  | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 5.5 | 1733 | 9531.5 | ac | 5.5 | 1733 | 9531.5 | ac | 5.5 | 1733 | 9531.5
2f2 |  |  | Rip
2f3 |  |  | Cover
2f4 |  |  | Growth Medium
Sloped
2f5 |  |  | Contour
2f6 |  |  | Rip
2f7 |  |  | Cover
2f8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 5.5 | 1733 | 9531.5 | ac | 5.5 | 1733 | 9531.5 | ac | 5.5 | 1733 | 9531.5
Flat
2f9 |  |  | Blade
2f10 |  |  | Seeding (seed, equipment, labor) |  |  | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 5.5 | 1500 | 8250 | ac | 5.5 | 1500 | 8250 | ac | 5.5 | 1500 | 8250
Sloped
2f11 |  |  | Blade
2f12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 5.5 | 1500 | 8250 | ac | 5.5 | 1500 | 8250 | ac | 5.5 | 1500 | 8250
| Borrow MB-Pit 2 Subtotal |  |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 5.5 | 3233 | 17781.5 | ac | 5.5 | 3233 | 17781.5 | ac | 5.5 | 3233 | 17781.5
2g | Borrow # 3-4
Flat
2g1 |  |  | Contour |  | 10190 | 33780.852 |  | 43970.852 | ac | 42 | 1046.925 | 43970.852 | ac | 42 | 1046.925 | 43970.852 | ac | 42 | 1570.3876 | 65956.278 | ac | 42 | 1570.3876 | 65956.278 | ac | 42 | 1570.3876 | 65956.278
2g2 |  |  | Rip
2g3 |  |  | Cover
2g4 |  |  | Growth Medium
Sloped
2g5 |  |  | Contour | [8 empty] | 0 |  |  |  | 0
2g6 |  |  | Rip
2g7 |  |  | Cover
2g8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 10190 | 33780.852 | 0 | 43970.852 | ac | 42 | 1046.925 | 43970.852 | ac | 42 | 1046.925 | 43970.852 | ac | 42 | 1570.3876 | 65956.278 | ac | 42 | 1570.3876 | 65956.278 | ac | 42 | 1570.3876 | 65956.278
Flat
2g9 |  |  | Blade
2g10 |  |  | Seeding (seed, equipment, labor) |  |  | 2252.04 | 4529.6559 | 6781.6959 | ac | 42 | 161.469 | 6781.6959 | ac | 42 | 161.469 | 6781.6959 | ac | 42 | 1500 | 63000 | ac | 42 | 1500 | 63000 | ac | 42 | 1500 | 63000
Sloped
2g11 |  |  | Blade
2g12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 2252.04 | 4529.6559 | 6781.6959 | ac | 42 | 161.469 | 6781.6959 | ac | 42 | 161.469 | 6781.6959 | ac | 42 | 1500 | 63000 | ac | 42 | 1500 | 63000 | ac | 42 | 1500 | 63000
| Borrow # 3-4 Subtotal |  |  |  | 10190 | 36032.892 | 4529.6559 | 50752.5479 | ac | 42 | 1208.394 | 50752.5479 | ac | 42 | 1208.394 | 50752.5479 | ac | 42 | 3070.3876 | 128956.278 | ac | 42 | 3070.3876 | 128956.278 | ac | 42 | 3070.3876 | 128956.278
2h | Borrow # 11
Flat
2h1 |  |  | Contour |  | 0 | 0 |  | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 29.5 | 1733 | 51123.5 | ac | 29.5 | 1733 | 51123.5 | ac | 29.5 | 1733 | 51123.5
2h2 |  |  | Rip
2h3 |  |  | Cover
2h4 |  |  | Growth Medium
Sloped
2h5 |  |  | Contour | [8 empty] | 0 |  |  |  | 0
2h6 |  |  | Rip
2h7 |  |  | Cover
2h8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 29.5 | 1733 | 51123.5 | ac | 29.5 | 1733 | 51123.5 | ac | 29.5 | 1733 | 51123.5
Flat
2h9 |  |  | Blade
2h10 |  |  | Seeding (seed, equipment, labor) |  |  | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 29.5 | 1500 | 44250 | ac | 29.5 | 1500 | 44250 | ac | 29.5 | 1500 | 44250
Sloped
2h11 |  |  | Blade
2h12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 29.5 | 1500 | 44250 | ac | 29.5 | 1500 | 44250 | ac | 29.5 | 1500 | 44250
| Borrow # 11 Subtotal |  |  |  | 0 | 0 | 0 | 0 | ac | 0 |  | 0 | ac | 0 |  | 0 | ac | 29.5 | 3233 | 95373.5 | ac | 29.5 | 3233 | 95373.5 | ac | 29.5 | 3233 | 95373.5
2i | Borrow # 2
Flat
2i1 |  |  | Contour |  | 1478 | 3705.36 |  | 5183.36 | ac | 8 | 647.92 | 5183.36 | ac | 8 | 647.92 | 5183.36 | ac | 8 | 971.88 | 7775.04 | ac | 8 | 971.88 | 7775.04 | ac | 8 | 971.88 | 7775.04
2i2 |  |  | Rip
2i3 |  |  | Cover
2i4 |  |  | Growth Medium
Sloped
2i5 |  |  | Contour
2i6 |  |  | Rip
2i7 |  |  | Cover
2i8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 1478 | 3705.36 | 0 | 5183.36 | ac | 8 | 647.92 | 5183.36 | ac | 8 | 647.92 | 5183.36 | ac | 8 | 971.88 | 7775.04 | ac | 8 | 971.88 | 7775.04 | ac | 8 | 971.88 | 7775.04
Flat
2i9 |  |  | Blade
2i10 |  |  | Seeding (seed, equipment, labor) |  |  | 428.96 | 862.7916 | 1291.7516 | ac | 8 | 161.469 | 1291.7516 | ac | 8 | 161.469 | 1291.7516 | ac | 8 | 1500 | 12000 | ac | 8 | 1500 | 12000 | ac | 8 | 1500 | 12000
Sloped
2i11 |  |  | Blade
2i12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 428.96 | 862.7916 | 1291.7516 | ac | 8 | 161.469 | 1291.7516 | ac | 8 | 161.469 | 1291.7516 | ac | 8 | 1500 | 12000 | ac | 8 | 1500 | 12000 | ac | 8 | 1500 | 12000
| Borrow # 2 Subtotal |  |  |  | 1478 | 4134.32 | 862.7916 | 6475.1116 | ac | 8 | 809.389 | 6475.1116 | ac | 8 | 809.389 | 6475.1116 | ac | 8 | 2471.88 | 19775.04 | ac | 8 | 2471.88 | 19775.04 | ac | 8 | 2471.88 | 19775.04
2j | Solo Creek / Tailing Dam
Flat
2j1 |  |  | Contour |  | 21750 | 38041.056 |  | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056
2j2 |  |  | Rip
2j3 |  |  | Cover
2j4 |  |  | Growth Medium
Sloped
2j5 |  |  | Contour
2j6 |  |  | Rip
2j7 |  |  | Cover
2j8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 21750 | 38041.056 | 0 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056 | ac | 107 | 558.7949 | 59791.056
Flat
2j9 |  |  | Blade
2j10 |  |  | Seeding (seed, equipment, labor) |  |  | 7721.28 | 11539.8378 | 19261.1178 | ac | 107 | 180.0104 | 19261.1178 | ac | 107 | 180.0104 | 19261.1178 | ac | 107 | 1500 | 160500 | ac | 107 | 1500 | 160500 | ac | 107 | 1500 | 160500
Sloped
2j11 |  |  | Blade
2j12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 7721.28 | 11539.8378 | 19261.1178 | ac | 107 | 180.0104 | 19261.1178 | ac | 107 | 180.0104 | 19261.1178 | ac | 107 | 1500 | 160500 | ac | 107 | 1500 | 160500 | ac | 107 | 1500 | 160500
| Solo Creek / Tailing Dam Subtotal |  |  |  | 21750 | 45762.336 | 11539.8378 | 79052.1738 | ac | 107 | 738.8054 | 79052.1738 | ac | 107 | 738.8054 | 79052.1738 | ac | 107 | 2058.7949 | 220291.056 | ac | 107 | 2058.7949 | 220291.056 | ac | 107 | 2058.7949 | 220291.056
2k | Borrow # 14
Flat
2k1 |  |  | Contour |  | 8253 | 28618.496 |  | 36871.496 | ac | 32 | 1152.2342 | 36871.496 | ac | 32 | 1152.2342 | 36871.496 | ac | 32 | 1728.3514 | 55307.244 | ac | 32 | 1728.3514 | 55307.244 | ac | 32 | 1728.3514 | 55307.244
2k2 |  |  | Rip
2k3 |  |  | Cover
2k4 |  |  | Growth Medium
Sloped
2k5 |  |  | Contour
2k6 |  |  | Rip
2k7 |  |  | Cover
2k8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 8253 | 28618.496 | 0 | 36871.496 | ac | 32 | 1152.2342 | 36871.496 | ac | 32 | 1152.2342 | 36871.496 | ac | 32 | 1728.3514 | 55307.244 | ac | 32 | 1728.3514 | 55307.244 | ac | 32 | 1728.3514 | 55307.244
Flat
2k9 |  |  | Blade
2k10 |  |  | Seeding (seed, equipment, labor) |  |  | 1715.84 | 3451.1664 | 5167.0064 | ac | 32 | 161.469 | 5167.0064 | ac | 32 | 161.469 | 5167.0064 | ac | 32 | 1500 | 48000 | ac | 32 | 1500 | 48000 | ac | 32 | 1500 | 48000
Sloped
2k11 |  |  | Blade
2k12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 0 | 1715.84 | 3451.1664 | 5167.0064 | ac | 32 | 161.469 | 5167.0064 | ac | 32 | 161.469 | 5167.0064 | ac | 32 | 1500 | 48000 | ac | 32 | 1500 | 48000 | ac | 32 | 1500 | 48000
| Borrow # 14 Subtotal |  |  |  | 8253 | 30334.336 | 3451.1664 | 42038.5024 | ac | 32 | 1313.7032 | 42038.5024 | ac | 32 | 1313.7032 | 42038.5024 | ac | 32 | 3228.3514 | 103307.244 | ac | 32 | 3228.3514 | 103307.244 | ac | 32 | 3228.3514 | 103307.244
| Subtotal Borrow Area Reclamation |  |  |  | 80652 | 270503.89 | 34565.5888 | 385721.4788 | ac | 320.5 | 1203.4992 | 385721.4788 | ac | 320.5 | 1203.4992 | 385721.4788 | ac | 365 | 2993.7071 | 1092703.082 | ac | 365 | 2993.7071 | 1092703.082 | ac | 365 | 2993.7071 | 1092703.082
3 | Open Pit Reclamation
3a | Highwall reduction
3b | Regrade open pit surfaces
3c | Construct perimeter berm |  |  |  | 4097 | 9755 | 0 | 13852 | ac | 37 | 374.3784 | 13852 | ac | 37 | 374.3784 | 13852 | ac | 37 | 374.3784 | 13852 | ac | 37 | 374.3784 | 13852 | ac | 37 | 374.3784 | 13852
3d | Haul and spread cover
3d1 |  | NAG Thickness
3d2 |  | Haul and spread NAG
3d3 |  | Size and amend growth-medium
3d4 |  | Haul and spread growth-medium (18-inches)
3e | Sub-total haul and spread cover
3f | Revegetate and weed control |  |  |  | 1486 | 1984 | 3971 | 7441 | ac | 37 | 201.1081 | 7441 | ac | 37 | 201.1081 | 7441 | ac | 37 | 1500 | 55500 | ac | 37 | 1500 | 55500 | ac | 37 | 1500 | 55500
3g | Install stormwater controls
3h | Install additional groundwater controls
| Subtotal Open Pit Area Reclamation |  |  |  | 5583 | 11739 | 3971 | 21293 | ac | 37 | 575.4865 | 21293 | ac | 37 | 575.4865 | 21293 | ac | 37 | 1874.3784 | 69352 | ac | 37 | 1874.3784 | 69352 | ac | 37 | 1874.3784 | 69352
4 | Facilities, Roads,and Other
4a | Haul Roads
Flat
4a1 |  |  | Contour |  | 19924 | 52842 |  | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766
4a2 |  |  | Rip
4a3 |  |  | Cover
4a4 |  |  | Growth Medium
Sloped
4a5 |  |  | Contour
4a6 |  |  | Rip
4a7 |  |  | Cover
4a8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 19924 | 52842 | 0 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766 | ac | 152 | 478.7237 | 72766
Flat
4a9 |  |  | Blade
4a10 |  |  | Seeding (seed, equipment, labor) |  | 6106 | 8150 | 16393 | 30649 | ac | 152 | 201.6382 | 30649 | ac | 152 | 201.6382 | 30649 | ac | 152 | 1500 | 228000 | ac | 152 | 1500 | 228000 | ac | 152 | 1500 | 228000
Sloped
4a11 |  |  | Blade
4a12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 6106 | 8150 | 16393 | 30649 | ac | 152 | 201.6382 | 30649 | ac | 152 | 201.6382 | 30649 | ac | 152 | 1500 | 228000 | ac | 152 | 1500 | 228000 | ac | 152 | 1500 | 228000
| Haul Roads Subtotal |  |  |  | 26030 | 60992 | 16393 | 103415 | ac | 152 | 680.3618 | 103415 | ac | 152 | 680.3618 | 103415 | ac | 152 | 1978.7237 | 300766 | ac | 152 | 1978.7237 | 300766 | ac | 152 | 1978.7237 | 300766
4b | Dismantling and equipment removal
4b1 |  | Removal and/or Demolition |  |  | 21209 | 63357 |  | 84566 | sf | 154882 | 0.546 | 84566 | sf | 154882 | 0.546 | 84566
|  |  | Buildings | [13 empty] | cf | 4646460 | 0.19 | 882827.4 | cf | 4646460 | 0.19 | 882827.4 | cf | 4646460 | 0.19 | 882827.4
|  |  | Foundation | [13 empty] | sf | 154882 | 0.75 | 116161.5 | sf | 154882 | 0.75 | 116161.5 | sf | 154882 | 0.75 | 116161.5
Flat
4b2 |  |  | Contour |  | 2676 | 14393 |  | 17069 | sf | 154882 | 0.11021 | 17069 | sf | 154882 | 0.11021 | 17069 | ac | 3.56 | 4794.6629 | 17069 | ac | 3.56 | 4794.6629 | 17069 | ac | 3.56 | 4794.6629 | 17069
4b3 |  |  | Rip
4b4 |  |  | Cover
4b5 |  |  | Growth Medium
Sloped
4b6 |  |  | Contour
4b7 |  |  | Rip
4b8 |  |  | Cover
4b9 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 2676 | 14393 | 0 | 17069 | sf | 154882 | 0.11021 | 17069 | sf | 154882 | 0.11021 | 17069 | ac | 3.56 | 4794.6629 | 17069 | sf | 3.56 | 4794.6629 | 17069 | sf | 3.56 | 4794.6629 | 17069
Flat
4b10 |  |  | Blade
4b11 |  |  | Seeding (seed, equipment, labor) |  | 143 | 191 | 384 | 718 | sf | 154882 | 0.0046358 | 718 | sf | 154882 | 0.0046358 | 718 | ac | 3.56 | 1500 | 5340 | ac | 3.56 | 201.6854 | 718 | ac | 3.56 | 201.6854 | 718
Sloped
4b12 |  |  | Blade
4b13 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 143 | 191 | 384 | 718 | sf | 154882 | 0.0046358 | 718 | sf | 154882 | 0.0046358 | 718 | ac | 3.56 | 201.6854 | 718 | ac | 3.56 | 201.6854 | 718 | ac | 3.56 | 201.6854 | 718
4b14 |  | Clean-up Trash and Debris | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Dismantling and equipment removal Subtotal |  |  |  | 24028 | 77941 | 384 | 102353 | sf | 154882 | 0.66085 | 102353 | sf | 154882 | 0.66085 | 102353 | ac | 3.56 | 285611.2079 | 1016775.9 | ac | 3.56 | 285611.2079 | 1016775.9 | ac | 3.56 | 285611.2079 | 1016775.9
4c | Miscellaneous Sites - Millsite
Flat
4c1 |  |  | Contour |  | 10886.08 | 44716.4 |  | 55602.48 | ac | 50 | 1112.0496 | 55602.48 | ac | 50 | 1112.0496 | 55602.48 | ac | 50 | 1668.0744 | 83403.72 | ac | 50 | 1668.0744 | 83403.72 | ac | 50 | 1668.0744 | 83403.72
4c2 |  |  | Rip
4c3 |  |  | Cover
4c4 |  |  | Growth Medium
Sloped
4c5 |  |  | Contour
4c6 |  |  | Rip
4c7 |  |  | Cover
4c8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 10886.08 | 44716.4 | 0 | 55602.48 | ac | 50 | 1112.0496 | 55602.48 | ac | 50 | 1112.0496 | 55602.48 | ac | 50 | 1668.0744 | 83403.72 | ac | 50 | 1668.0744 | 83403.72 | ac | 50 | 1668.0744 | 83403.72
Flat
4c9 |  |  | Blade
4c10 |  |  | Seeding (seed, equipment, labor) |  | 2008.5 | 2681 | 5392.5 | 10082 | ac | 50 | 201.64 | 10082 | ac | 50 | 201.64 | 10082 | ac | 50 | 1500 | 75000 | ac | 50 | 1500 | 75000 | ac | 50 | 1500 | 75000
Sloped
4c11 |  |  | Blade
4c12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 2008.5 | 2681 | 5392.5 | 10082 | ac | 50 | 201.64 | 10082 | ac | 50 | 201.64 | 10082 | ac | 50 | 1500 | 75000 | ac | 50 | 1500 | 75000 | ac | 50 | 1500 | 75000
| Miscellaneous Sites - Millsite Subtotal |  |  |  | 12894.58 | 47397.4 | 5392.5 | 65684.48 | ac | 50 | 1313.6896 | 65684.48 | ac | 50 | 1313.6896 | 65684.48 | ac | 50 | 3168.0744 | 158403.72 | ac | 50 | 3168.0744 | 158403.72 | ac | 50 | 3168.0744 | 158403.72
4d | Miscellaneous Sites - Conveyor Crossing
Flat
4d1 |  |  | Contour |  | 5075.07 | 20846.79 |  | 25921.86 | ac | 23.31 | 1112.0489 | 25921.86 | ac | 23.31 | 1112.0489 | 25921.86 | ac | 23.31 | 1668.0734 | 38882.79 | ac | 23.31 | 1668.0734 | 38882.79 | ac | 23.31 | 1668.0734 | 38882.79
4d2 |  |  | Rip
4d3 |  |  | Cover
4d4 |  |  | Growth Medium
Sloped
4d5 |  |  | Contour
4d6 |  |  | Rip
4d7 |  |  | Cover
4d8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 5075.07 | 20846.79 | 0 | 25921.86 | ac | 23.31 | 1112.0489 | 25921.86 | ac | 23.31 | 1112.0489 | 25921.86 | ac | 23.31 | 1668.0734 | 38882.79 | ac | 23.31 | 1668.0734 | 38882.79 | ac | 23.31 | 1668.0734 | 38882.79
Flat
4d9 |  |  | Blade
4d10 |  |  | Seeding (seed, equipment, labor) |  | 936.36 | 1249.88 | 2513.98 | 4700.22 | ac | 23.31 | 201.6396 | 4700.22 | ac | 23.31 | 201.6396 | 4700.22 | ac | 23.31 | 1500 | 34965 | ac | 23.31 | 1500 | 34965 | ac | 23.31 | 1500 | 34965
Sloped
4d11 |  |  | Blade
4d12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 936.36 | 1249.88 | 2513.98 | 4700.22 | ac | 23.31 | 201.6396 | 4700.22 | ac | 23.31 | 201.6396 | 4700.22 | ac | 23.31 | 1500 | 34965 | ac | 23.31 | 1500 | 34965 | ac | 23.31 | 1500 | 34965
| Miscellaneous Sites - Conveyor Crossing Subtotal |  |  |  | 6011.43 | 22096.67 | 2513.98 | 30622.08 | ac | 23.31 | 1313.6885 | 30622.08 | ac | 23.31 | 1313.6885 | 30622.08 | ac | 23.31 | 3168.0734 | 73847.79 | ac | 23.31 | 3168.0734 | 73847.79 | ac | 23.31 | 3168.0734 | 73847.79
4e | Miscellaneous Sites - Crusher Station
Flat
4e1 |  |  | Contour |  | 3265.82 | 13414.93 |  | 16680.75 | ac | 15 | 1112.05 | 16680.75 | ac | 15 | 1112.05 | 16680.75 | ac | 15 | 1668.075 | 25021.125 | ac | 15 | 1668.075 | 25021.125 | ac | 15 | 1668.075 | 25021.125
4e2 |  |  | Rip
4e3 |  |  | Cover
4e4 |  |  | Growth Medium
Sloped
4e5 |  |  | Contour
4e6 |  |  | Rip
4e7 |  |  | Cover
4e8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 3265.82 | 13414.93 | 0 | 16680.75 | ac | 15 | 1112.05 | 16680.75 | ac | 15 | 1112.05 | 16680.75 | ac | 15 | 1668.075 | 25021.125 | ac | 15 | 1668.075 | 25021.125 | ac | 15 | 1668.075 | 25021.125
Flat
4e9 |  |  | Blade
4e10 |  |  | Seeding (seed, equipment, labor) |  | 602.55 | 804.3 | 1617.75 | 3024.6 | ac | 15 | 201.64 | 3024.6 | ac | 15 | 201.64 | 3024.6 | ac | 15 | 1500 | 22500 | ac | 15 | 1500 | 22500 | ac | 15 | 1500 | 22500
Sloped
4e11 |  |  | Blade
4e12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 602.55 | 804.3 | 1617.75 | 3024.6 | ac | 15 | 201.64 | 3024.6 | ac | 15 | 201.64 | 3024.6 | ac | 15 | 1500 | 22500 | ac | 15 | 1500 | 22500 | ac | 15 | 1500 | 22500
| Miscellaneous Sites - Crusher Station Subtotal |  |  |  | 3868.37 | 14219.23 | 1617.75 | 19705.35 | ac | 15 | 1313.69 | 19705.35 | ac | 15 | 1313.69 | 19705.35 | ac | 15 | 3168.075 | 47521.125 | ac | 15 | 3168.075 | 47521.125 | ac | 15 | 3168.075 | 47521.125
4f | Miscellaneous Sites - Pit Diversion Ditches
Flat
4f1 |  |  | Contour |  | 5321.72 | 12680.35 |  | 18002.07 | ac | 48 | 375.0431 | 18002.07 | ac | 48 | 375.0431 | 18002.07 | ac | 48 | 562.5647 | 27003.105 | ac | 48 | 562.5647 | 27003.105 | ac | 48 | 562.5647 | 27003.105
4f2 |  |  | Rip
4f3 |  |  | Cover
4f4 |  |  | Growth Medium
Sloped
4f5 |  |  | Contour
4f6 |  |  | Rip
4f7 |  |  | Cover
4f8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 5321.72 | 12680.35 | 0 | 18002.07 | ac | 48 | 375.0431 | 18002.07 | ac | 48 | 375.0431 | 18002.07 | ac | 48 | 562.5647 | 27003.105 | ac | 48 | 562.5647 | 27003.105 | ac | 48 | 562.5647 | 27003.105
Flat
4f9 |  |  | Blade
4f10 |  |  | Seeding (seed, equipment, labor) |  | 1928.16 | 2573.76 | 5176.8 | 9678.72 | ac | 48 | 201.64 | 9678.72 | ac | 48 | 201.64 | 9678.72 | ac | 48 | 1500 | 72000 | ac | 48 | 1500 | 72000 | ac | 48 | 1500 | 72000
Sloped
4f11 |  |  | Blade
4f12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 1928.16 | 2573.76 | 5176.8 | 9678.72 | ac | 48 | 201.64 | 9678.72 | ac | 48 | 201.64 | 9678.72 | ac | 48 | 1500 | 72000 | ac | 48 | 1500 | 72000 | ac | 48 | 1500 | 72000
| Miscellaneous Sites - Pit Diversion Ditches Subtotal |  |  |  | 7249.88 | 15254.11 | 5176.8 | 27680.79 | ac | 48 | 576.6831 | 27680.79 | ac | 48 | 576.6831 | 27680.79 | ac | 48 | 2062.5647 | 99003.105 | ac | 48 | 2062.5647 | 99003.105 | ac | 48 | 2062.5647 | 99003.105
4g | Miscellaneous Sites - Wetlands
Flat
4g1 |  |  | Contour |  | 7428.24 | 17699.66 |  | 25127.9 | ac | 67 | 375.0433 | 25127.9 | ac | 67 | 375.0433 | 25127.9 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500
4g2 |  |  | Rip
4g3 |  |  | Cover
4g4 |  |  | Growth Medium
Sloped
4g5 |  |  | Contour
4g6 |  |  | Rip
4g7 |  |  | Cover
5g8 |  |  | Growth Medium
|  | Earthwork/Recontouring Subtotal |  |  | 7428.24 | 17699.66 | 0 | 25127.9 | ac | 67 | 375.0433 | 25127.9 | ac | 67 | 375.0433 | 25127.9 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500
Flat
4g9 |  |  | Blade
4g10 |  |  | Seeding (seed, equipment, labor) |  | 2691.39 | 3592.54 | 7225.95 | 13509.88 | ac | 67 |  | 13509.88 | ac | 67 |  | 13509.88 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500
Sloped
4g11 |  |  | Blade
4g12 |  |  | Seeding (seed + equipment + labor)
|  | Revegetation/Stabilization Subtotal |  |  | 2691.39 | 3592.54 | 7225.95 | 13509.88 | ac | 67 | 201.64 | 13509.88 | ac | 67 | 201.64 | 13509.88 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500 | ac | 67 | 1500 | 100500
| Miscellaneous Sites - Wetlands Subtotal |  |  |  | 10119.63 | 21292.2 | 7225.95 | 38637.78 | ac | 67 | 576.6833 | 38637.78 | ac | 67 | 576.6833 | 38637.78 | ac | 67 | 3000 | 201000 | ac | 67 | 3000 | 201000 | ac | 67 | 3000 | 201000
4h | Install stormwater controls
| Subtotal Facilities, Roads, Borrow Areas and Other |  |  |  | 90201.89 | 259192.61 | 38703.98 | 388098.48 | ac | 355.31 | 1092.2813 | 388098.48 | ac | 355.31 | 1092.2813 | 388098.48 | ac | 355.31 | 5339.8937 | 1897317.64 | ac | 355.31 | 5339.8937 | 1897317.64 | ac | 355.31 | 5339.8937 | 1897317.64
5 | Miscellaneous
5a | Detoxification/Disposal of Wastes
5b | Public Safety
| Subtotal Miscellaneous | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
6 | Water Treatment Capture, Pump, Treatment and Discharge
6a | Interceptor wells
6b | Collection and distribution
6c | Degritting/equilization ponds
6d | Water treatment plant
6e | Sludge disposal facilities
6f | Effluent disposal facilities
| Subtotal Water Treatment Capture, Pump, Treatment and Discharge | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Total Tasks 1 thru 6 |  |  |  | 316428.89 | 1104609.5 | 116260.5688 | 1537298.9588 | ac | 1064.91 | 1443.5952 | 1537298.9588 | ac | 1064.91 | 1443.5952 | 1537298.9588 | ac | 1109.41 | 4271.4192 | 4738755.222 | ac | 1109.41 | 4271.4192 | 4738755.222 | ac | 1109.41 | 4271.4192 | 4738755.222
7 | Indirect Costs
7a | Contingency |  |  | 5% | 15821.4445 | 55230.475 | 5813.0284 | 76864.9479 |  |  |  | 76864.9479 | 5% |  |  | 76864.9479 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611
7b | Mobilization and demobilization |  |  | 5% | 15821.4445 | 55230.475 | 5813.0284 | 76864.9479 |  |  |  | 76864.9479 | 5% |  |  | 76864.9479 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611
7c | Engineering redesign | [11 empty] | 3% |  |  | 46118.9688 | 3% |  |  | 142162.6567 | 3% |  |  | 142162.6567 | 3% |  |  | 142162.6567
7d | Engineering, procurement, construction management | [11 empty] | 5% |  |  | 76864.9479 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611
7e | Contractor Overhead | [11 empty] | 15% |  |  | 230594.8438 | 15% |  |  | 710813.2833 | 15% |  |  | 710813.2833 | 15% |  |  | 710813.2833
7f | Contractor Profit |  |  | 10% | 31642.889 | 110460.95 | 11626.0569 | 153729.8959 |  |  |  | 153729.8959 | 10% |  |  | 153729.8959 | 10% |  |  | 473875.5222 | 10% |  |  | 473875.5222 | 10% |  |  | 473875.5222
7g | Agency Administration |  |  | 5% | 15821.4445 | 55230.475 | 5813.0284 | 76864.9479 |  |  |  | 76864.9479 | 5% |  |  | 76864.9479 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611 | 5% |  |  | 236937.7611
7h | Inflation |  |  | 8% | 25314.3112 | 88368.76 | 9300.8455 | 122983.9167 |  |  |  | 122983.9167 | 3% |  |  | 46118.9688 | 3% |  |  | 142162.6567 | 3% |  |  | 142162.6567 | 3% |  |  | 142162.6567
| Sub-Total Indirect Costs | [6 empty] | 507308.6564 |  |  | 33% | 507308.6564 |  |  | 51% | 784022.469 |  |  | 51% | 2416765.1632 |  |  | 51% | 2416765.1632 |  |  | 51% | 2416765.1632
Total Capital Cost |  |  |  |  | 316428.89 | 1104609.5 | 116260.5688 | 2044607.6152 | ac | 1064.91 | 1919.9816 | 2044607.6152 | ac | 1064.91 | 2179.8287 | 2321321.4278 | ac | 1109.41 | 6449.8431 | 7155520.3852 | ac | 1109.41 | 6449.8431 | 7155520.3852 | ac | 1109.41 | 6449.8431 | 7155520.3852
Total Cost | [7 empty] | 2105383.2952 | ac | 1064.91 | 1977.0528 | 2105383.2952 | ac | 1064.91 | 2244.6239 | 2390322.3878 | ac | 1109.41 | 6512.0391 | 7224521.3452 | ac | 1109.41 | 6512.0391 | 7224521.3452 | ac | 1109.41 | 6512.0391 | 7224521.3452
SUMMARY - Fort Knox Mine Reclamation Plan
Item1 | Mine Waste Pile Reclamation
|  | Yellow Pup Dump |  |  | 48777.75 | 176230.32 | 17696.7406 | 242704.8106 | ac | 120 | 2022.5401 | 242704.8106 | ac | 120 | 2296.2673 | 275552.0782 | ac | 120 | 5837.0875 | 700450.495 | ac | 120 | 5837.0875 | 700450.495 | ac | 120 | 5837.0875 | 700450.495
|  | Barnes Creek Dump |  |  | 100997.54 | 421001.4585 | 25117.9544 | 547116.9529 | ac | 170.5 | 3208.8971 | 547116.9529 | ac | 170.5 | 3643.1839 | 621162.8563 | ac | 170.5 | 7903.7398 | 1347587.6276 | ac | 170.5 | 7903.7398 | 1347587.6276 | ac | 170.5 | 7903.7398 | 1347587.6276
|  | Lowgrade Stockpile |  |  | 36414.07 | 151789.6415 | 9081.905 | 197285.6165 | ac | 61.6 | 3202.6886 | 197285.6165 | ac | 61.6 | 3636.1352 | 223985.9255 | ac | 61.6 | 7919.3093 | 487829.4524 | ac | 61.6 | 7919.3093 | 487829.4524 | ac | 61.6 | 7919.3093 | 487829.4524
|  | Install additional stormwater controls |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Install additional groundwater controls |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Subtotal Waste Rock Area Reclamation |  |  |  | 186189.36 | 749021.42 | 51896.6 | 987107.38 | ac | 352.1 | 2803.4859 | 987107.38 | ac | 352.1 | 3182.905 | 1120700.86 | ac | 352.1 | 7202.1232 | 2535867.575 | ac | 352.1 | 7202.1232 | 2535867.575 | ac | 352.1 | 7202.1232 | 2535867.575
Item 2 | Borrow Area Reclamation
|  | Borrow # 12 |  |  | 10633.35 | 39083.896 | 4446.6123 | 54163.8583 | ac | 31 | 1747.2212 | 54163.8583 | ac | 31 | 1983.6873 | 61494.3053 | ac | 31 | 4874.8037 | 151118.9155 | ac | 31 | 4874.8037 | 151118.9155 | ac | 31 | 4874.8037 | 151118.9155
|  | Laydown Yard |  |  | 7466.62 | 24580.0958 | 3585.9776 | 35632.6934 | ac | 25 | 1425.3077 | 35632.6934 | ac | 25 | 1618.2065 | 40455.1632 | ac | 25 | 4326.5826 | 108164.5654 | ac | 25 | 4326.5826 | 108164.5654 | ac | 25 | 4326.5826 | 108164.5654
|  | Aggregate Crusher |  |  | 3601.64 | 13240.3003 | 1506.1106 | 18348.0509 | ac | 10.5 | 1747.4334 | 18348.0509 | ac | 10.5 | 1983.9282 | 20831.2457 | ac | 10.5 | 4875.1651 | 51189.2333 | ac | 10.5 | 4875.1651 | 51189.2333 | ac | 10.5 | 4875.1651 | 51189.2333
|  | Borrow # 5 |  |  | 30143.12 | 128234.9159 | 9323.5418 | 167701.5777 | ac | 65 | 2580.0243 | 167701.5777 | ac | 65 | 2929.2005 | 190398.0318 | ac | 65 | 6293.0736 | 409049.7815 | ac | 65 | 6293.0736 | 409049.7815 | ac | 65 | 6293.0736 | 409049.7815
|  | Borrow MB-Pit 1 & Scenic Overlook |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 46377.385 |  |  |  | 46377.385 |  |  |  | 46377.385
|  | Borrow MB-Pit 2 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 26850.065 |  |  |  | 26850.065 |  |  |  | 26850.065
|  | Borrow # 3-4 |  |  | 13552.7 | 47923.7464 | 6024.4424 | 67500.8888 | ac | 42 | 1607.164 | 67500.8888 | ac | 42 | 1824.6749 | 76636.3474 | ac | 42 | 4636.2852 | 194723.9798 | ac | 42 | 4636.2852 | 194723.9798 | ac | 42 | 4636.2852 | 194723.9798
|  | Borrow # 11 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 144013.985 |  |  |  | 144013.985 |  |  |  | 144013.985
|  | Borrow # 2 |  |  | 1965.74 | 5498.6456 | 1147.5128 | 8611.8984 | ac | 8 | 1076.4873 | 8611.8984 | ac | 8 | 1222.1773 | 9777.4185 | ac | 8 | 3732.5388 | 29860.3104 | ac | 8 | 3732.5388 | 29860.3104 | ac | 8 | 3732.5388 | 29860.3104
|  | Solo Creek / Tailing Dam |  |  | 28927.5 | 60863.9069 | 15347.9842 | 105139.3911 | ac | 107 | 982.6111 | 105139.3911 | ac | 107 | 1115.5961 | 119368.7824 | ac | 107 | 3108.7803 | 332639.4946 | ac | 107 | 3108.7803 | 332639.4946 | ac | 107 | 3108.7803 | 332639.4946
|  | Borrow # 14 |  |  | 10976.49 | 40344.6669 | 4590.0514 | 55911.2082 | ac | 32 | 1747.2253 | 55911.2082 | ac | 32 | 1983.6918 | 63478.1387 | ac | 32 | 4874.8106 | 155993.9384 | ac | 32 | 4874.8106 | 155993.9384 | ac | 32 | 4874.8106 | 155993.9384
| Subtotal Borrow Area Reclamation |  |  |  | 107267.16 | 359770.1737 | 45972.2331 | 513009.5668 | ac | 320.5 | 1600.6539 | 513009.5668 | ac | 320.5 | 1817.2837 | 582439.433 | ac | 365 | 4520.4977 | 1649981.6538 | ac | 365 | 4520.4977 | 1649981.6538 | ac | 365 | 4520.4977 | 1649981.6538
Item 3 | Open Pit Reclamation |  |  |  | 7425.39 | 15612.87 | 5281.43 | 28319.69 | ac | 37 | 765.397 | 28319.69 | ac | 37 | 868.9846 | 32152.43 | ac | 37 | 2830.3114 | 104721.52 | ac | 37 | 2830.3114 | 104721.52 | ac | 37 | 2830.3114 | 104721.52
Item 4 | Facilities, Roads,and Other
|  | Haul Roads |  |  | 34619.9 | 81119.36 | 21802.69 | 137541.95 | ac | 152 | 904.8813 | 137541.95 | ac | 152 | 1027.3464 | 156156.65 | ac | 152 | 2987.8728 | 454156.66 | ac | 152 | 2987.8728 | 454156.66 | ac | 152 | 2987.8728 | 454156.66
|  | Dismantling and equipment removal |  |  | 31957.24 | 103661.53 | 510.72 | 136129.49 | sf | 154882 | 0.87892 | 136129.49 | sf | 154882 | 0.99788 | 154553.03 | ac | 3.56 | 431272.9239 | 1535331.609 | ac | 3.56 | 431272.9239 | 1535331.609 | ac | 3.56 | 431272.9239 | 1535331.609
|  | Miscellaneous Sites - Millsite |  |  | 17149.7914 | 63038.542 | 7172.025 | 87360.3584 | ac | 50 | 1747.2072 | 87360.3584 | ac | 50 | 1983.6713 | 99183.5648 | ac | 50 | 4783.7923 | 239189.6172 | ac | 50 | 4783.7923 | 239189.6172 | ac | 50 | 4783.7923 | 239189.6172
|  | Miscellaneous Sites - Conveyor Crossing |  |  | 7995.2019 | 29388.5711 | 3343.5934 | 40727.3664 | ac | 23.31 | 1747.2058 | 40727.3664 | ac | 23.31 | 1983.6697 | 46239.3408 | ac | 23.31 | 4783.7908 | 111510.1629 | ac | 23.31 | 4783.7908 | 111510.1629 | ac | 23.31 | 4783.7908 | 111510.1629
|  | Miscellaneous Sites - Crusher Station |  |  | 5144.9321 | 18911.5759 | 2151.6075 | 26208.1155 | ac | 15 | 1747.2077 | 26208.1155 | ac | 15 | 1983.6719 | 29755.0785 | ac | 15 | 4783.7932 | 71756.8987 | ac | 15 | 4783.7932 | 71756.8987 | ac | 15 | 4783.7932 | 71756.8987
|  | Miscellaneous Sites - Pit Diversion Ditches |  |  | 9642.3404 | 20287.9663 | 6885.144 | 36815.4507 | ac | 48 | 766.9886 | 36815.4507 | ac | 48 | 870.7915 | 41797.9929 | ac | 48 | 3114.4727 | 149494.6885 | ac | 48 | 3114.4727 | 149494.6885 | ac | 48 | 3114.4727 | 149494.6885
|  | Miscellaneous Sites - Wetlands |  |  | 13459.1079 | 28318.626 | 9610.5135 | 51388.2474 | ac | 67 | 766.9888 | 51388.2474 | ac | 67 | 870.7918 | 58343.0478 | ac | 67 | 4530 | 303510 | ac | 67 | 4530 | 303510 | ac | 67 | 4530 | 303510
|  | Install stormwater controls |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Subtotal Facilities, Roads, Borrow Areas and Other |  |  |  | 119968.5137 | 344726.1713 | 51476.2934 | 516170.9784 | ac | 355.31 | 1452.7342 | 516170.9784 | ac | 355.31 | 1649.3448 | 586028.7048 | ac | 355.31 | 8063.2395 | 2864949.6364 | ac | 355.31 | 8063.2395 | 2864949.6364 | ac | 355.31 | 8063.2395 | 2864949.6364
Item 5 | Miscellaneous
|  | Detoxification/Disposal of Wastes |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Public Safety |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Subtotal Miscellaneous |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Item 6 | Water Treatment Capture, Pump, Treatment and Discharge |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Total Capital Reclamation Cost | [6 empty] | 2044607.6152 | ac | 1064.91 | 6622.271 | 2044607.6152 | ac | 1064.91 | 7518.5182 | 2321321.4278 | ac | 1109.41 | 22616.1717 | 7155520.3852 | ac | 1109.41 | 22616.1717 | 7155520.3852 | ac | 1109.41 | 22616.1717 | 7155520.3852
Note on C326: : excluding 70 acres? Note in summary
Note on J308: David M. Chambers: missing 37 acres in this portion of the estimate See Ft Knox worksheet

## Capital Cost Assumptions
Detailed Reclamation and Closure/Closeout Bond Cost Estimate - Capital Costs
Fort Knox Mine Reclamation Plan
|  | Tasks |  |  | Fort Knox Mine Reclamation Plan 2001 | CSP2 2003 Estimate - Scenario 1 | CSP2 2003 Estimate - Scenario 2 | CSP2 2003 Estimate - Scenario 3 | CSP2 2003 Estimate - Scenario 4
Line
[6 empty] | duplicate Ft Knox Rec. Plan captial and operating costs, changes to indirect costs as noted | assess and change reclamation tasks and unit costs as noted, indirect costs from CSP2 scenario 1 | same assumpitons as CSP2 scenario 2 with 50 years water treatment | same assumpitons as CSP2 scenario 2 with 100 years water treatment
1 | Mine Waste Pile Reclamation
1a | Yellow Pup Dump
|  | Flat |  |  | based on Dumps cost estimation sheet; 66.7% of labor on flat slopes
1a1 |  |  | Contour |  | based on Dumps cost estimation sheet; Yellow Pup flat areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1a2 |  |  | Rip
1a3 |  |  | Cover
1a4 |  |  | Growth Medium
|  | Sloped |  |  | based on Dumps cost estimation worksheet; 33.3% of labor on sloped surfaces
1a5 |  |  | Contour |  | based on Dumps cost estimation sheet; Yellow Pup sloped areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1a6 |  |  | Rip
1a7 |  |  | Cover
1a8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
1a9 |  |  | Blade
1a10 |  |  | Seeding (seed, equipment, labor) |  | based on Dumps cost estimation sheet; material cost is 34.1% of total materials |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
1a11 |  |  | Blade
1a12 |  |  | Seeding (seed + equipment + labor) |  | based on Dumps cost estimation sheet; material cost is 34.1% of total materials |  | unit cost based on MDEQ estimation for sloped surfaces
Revegetation/Stabilization Subtotal
Yellow Pup Dump Subtotal
1b | Barnes Creek Dump
|  | Flat |  |  | based on Dumps cost estimation worksheet; 63.6% of labor on flat surfaces; 73.5% of Barnes Cr + Lowgrade area
1b1 |  |  | Contour |  | based on Dumps cost estimation sheet; 73.5% of Barnes Cr/Lowgrade flat areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1b2 |  |  | Rip
1b3 |  |  | Cover
1b4 |  |  | Growth Medium
|  | Sloped |  |  | based on Dumps cost estimation worksheet; 36.4% of labor on sloped surfaces; 73.5% of Barnes Cr + Lowgrade area
1b5 |  |  | Contour |  | based on Dumps cost estimation sheet; 73.5% of Barnes Cr/Lowgrade sloped areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1b6 |  |  | Rip
1b7 |  |  | Cover
1b8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
1b9 |  |  | Blade
1b10 |  |  | Seeding (seed, equipment, labor) |  | based on Dumps cost estimation sheet; material cost is 48.4% of total materials |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
1b11 |  |  | Blade
1b12 |  |  | Seeding (seed + equipment + labor) |  | based on Dumps cost estimation sheet; material cost is 48.4% of total materials |  | unit cost based on MDEQ estimation for sloped surfaces
Revegetation/Stabilization Subtotal
Barnes Creek Dump Subtotal
1c | Lowgrade Stockpile
|  | Flat |  |  | based on Dumps cost estimation worksheet; 61.8% of labor on flat surfaces; 26.5% of Barnes Cr + Lowgrade area
1c1 |  |  | Contour |  | based on Dumps cost estimation sheet; 26.5% of Barnes Cr/Lowgrade flat areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1c2 |  |  | Rip
1c3 |  |  | Cover
1c4 |  |  | Growth Medium
|  | Sloped |  |  | based on Dumps cost estimation worksheet; 38.2% of labor on sloped surfaces; 26.5% of Barnes Cr + Lowgrade area
1c5 |  |  | Contour |  | based on Dumps cost estimation sheet; 26.5% of Barnes Cr/Lowgrade sloped areas |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Waste Rock Reclamation increased by 50%
1c6 |  |  | Rip
1c7 |  |  | Cover
1c8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
1c9 |  |  | Blade
1c10 |  |  | Seeding (seed, equipment, labor) |  | based on Dumps cost estimation sheet; material cost is 17.5% of total materials |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
1c11 |  |  | Blade
1c12 |  |  | Seeding (seed + equipment + labor) |  | based on Dumps cost estimation sheet; material cost is 17.5% of total materials |  | unit cost based on MDEQ estimation for sloped surfaces
Revegetation/Stabilization Subtotal
Lowgrade Stockpile Subtotal
1d | Install additional stormwater controls
1e | Install additional groundwater controls
Subtotal Waste Rock Area Reclamation
2 | Borrow Area Reclamation
2a | Borrow # 12 |  |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#12)
Flat
2a1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2a2 |  |  | Rip
2a3 |  |  | Cover
2a4 |  |  | Growth Medium
Sloped
2a5 |  |  | Contour
2a6 |  |  | Rip
2a7 |  |  | Cover
2a8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2a9 |  |  | Blade
2a10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2a11 |  |  | Blade
2a12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow #12 Subtotal
2b | Laydown Yard
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (laydown)
2b1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2b2 |  |  | Rip
2b3 |  |  | Cover
2b4 |  |  | Growth Medium
Sloped
2b5 |  |  | Contour
2b6 |  |  | Rip
2b7 |  |  | Cover
2b8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2b9 |  |  | Blade
2b10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2b11 |  |  | Blade
2b12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Laydown Yard Subtotal
2c | Aggregate Crusher
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (agg. crusher)
2c1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2c2 |  |  | Rip
2c3 |  |  | Cover
2c4 |  |  | Growth Medium
Sloped
2c5 |  |  | Contour
2c6 |  |  | Rip
2c7 |  |  | Cover
2c8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2c9 |  |  | Blade
2c10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2c11 |  |  | Blade
2c12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Aggregate Crusher Subtotal
2d | Borrow # 5
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#5)
2d1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2d2 |  |  | Rip
2d3 |  |  | Cover
2d4 |  |  | Growth Medium
Sloped
2d5 |  |  | Contour
2d6 |  |  | Rip
2d7 |  |  | Cover
2d8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2d9 |  |  | Blade
2d10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2d11 |  |  | Blade
2d12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow # 5 Subtotal
2e | Borrow MB-Pit 1 & Scenic Overlook | [5 empty] | conduct reclamation consistent with other borrow areas, acreage from Figure 1
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (MB-Pit/Scenic Overlook)
2e1 |  |  | Contour |  |  |  | unit cost of $1733/ac based on average unit cost for borrow areas with 12" growth media
2e2 |  |  | Rip
2e3 |  |  | Cover
2e4 |  |  | Growth Medium
Sloped
2e5 |  |  | Contour
2e6 |  |  | Rip
2e7 |  |  | Cover
2e8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2e9 |  |  | Blade
2e10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2e11 |  |  | Blade
2e12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow MB-Pit 1 & Scenic Overlook Subtotal
2f | Borrow MB-Pit 2 | [5 empty] | conduct reclamation consistent with other borrow areas, acreage from Figure 1
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (MB-Pit-2)
2f1 |  |  | Contour |  |  |  | unit cost of $1733/ac based on average unit cost for borrow areas with 12" growth media
2f2 |  |  | Rip
2f3 |  |  | Cover
2f4 |  |  | Growth Medium
Sloped
2f5 |  |  | Contour
2f6 |  |  | Rip
2f7 |  |  | Cover
2f8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2f9 |  |  | Blade
2f10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2f11 |  |  | Blade
2f12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow MB-Pit 2 Subtotal
2g | Borrow # 3-4
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#3-4)
2g1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2g2 |  |  | Rip
2g3 |  |  | Cover
2g4 |  |  | Growth Medium
Sloped
2g5 |  |  | Contour
2g6 |  |  | Rip
2g7 |  |  | Cover
2g8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2g9 |  |  | Blade
2g10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2g11 |  |  | Blade
2g12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow # 3-4 Subtotal
2h | Borrow # 11 | [5 empty] | conduct reclamation consistent with other borrow areas, acreage from Figure 1
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#11)
2h1 |  |  | Contour |  |  |  | unit cost of $1733/ac based on average unit cost for borrow areas with 12" growth media
2h2 |  |  | Rip
2h3 |  |  | Cover
2h4 |  |  | Growth Medium
Sloped
2h5 |  |  | Contour
2h6 |  |  | Rip
2h7 |  |  | Cover
2h8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2h9 |  |  | Blade
2h10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2h11 |  |  | Blade
2h12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow # 11 Subtotal
2i | Borrow # 2
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#2)
2i1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2i2 |  |  | Rip
2i3 |  |  | Cover
2i4 |  |  | Growth Medium
Sloped
2i5 |  |  | Contour
2i6 |  |  | Rip
2i7 |  |  | Cover
2i8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2i9 |  |  | Blade
2i10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2i11 |  |  | Blade
2i12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow # 2 Subtotal
2j | Solo Creek / Tailing Dam
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (Solo Ck/Tailing Dam)
2j1 |  |  | Contour
2j2 |  |  | Rip
2j3 |  |  | Cover
2j4 |  |  | Growth Medium
Sloped
2j5 |  |  | Contour
2j6 |  |  | Rip
2j7 |  |  | Cover
2j8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2j9 |  |  | Blade
2j10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2j11 |  |  | Blade
2j12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Solo Creek / Tailing Dam Subtotal
2k | Borrow # 14
|  | Flat |  |  | from Borrow/Spoil and Misc. Areas cost estimation worksheet (#14)
2k1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Borrow Area Reclamation increased by 50%
2k2 |  |  | Rip
2k3 |  |  | Cover
2k4 |  |  | Growth Medium
Sloped
2k5 |  |  | Contour
2k6 |  |  | Rip
2k7 |  |  | Cover
2k8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
2k9 |  |  | Blade
2k10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
2k11 |  |  | Blade
2k12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Borrow # 14 Subtotal
Subtotal Borrow Area Reclamation
3 | Open Pit Reclamation
3a | Highwall reduction
3b | Regrade open pit surfaces
3c | Construct perimeter berm |  |  |  | from Open Pit cost estimation worksheet
3d | Haul and spread cover
3d1 |  | NAG Thickness
3d2 |  | Haul and spread NAG
3d3 |  | Size and amend growth-medium
3d4 |  | Haul and spread growth-medium (18-inches)
3e | Sub-total haul and spread cover
3f | Revegetate and weed control |  |  |  | from Open Pit cost estimation worksheet |  | unit cost based on MDEQ estimation for flat surfaces
3g | Install stormwater controls
3h | Install additional groundwater controls
Subtotal Open Pit Area Reclamation
4 | Facilities, Roads, and Other
4a | Haul Roads |  |  |  | from Roads cost estimation worksheet
|  | Flat |  |  | assumption of flat surfaces for roads
4a1 |  |  | Contour
4a2 |  |  | Rip
4a3 |  |  | Cover
4a4 |  |  | Growth Medium
Sloped
4a5 |  |  | Contour
4a6 |  |  | Rip
4a7 |  |  | Cover
4a8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4a9 |  |  | Blade
4a10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4a11 |  |  | Blade
4a12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Haul Roads Subtotal
4b | Dismantling and equipment removal
4b1 |  | Removal and/or Demolition |  |  | from Building and Equipment Sites cost estimation worksheet |  | reclamation plan assumes buildings removed for salvage prior to cost estimation for demolition
|  |  | Buildings |  |  |  | unit cost of $0.19/cf based on RS Means 2001 demolition cost for steel buildings, assumes 30 ft height x 154882 sf for 4646460 cf
|  |  | Foundation |  |  |  | unit cost of $0.75/sf based on MDEQ demolition cost estimate for SMC East Boulder Mine
|  | Flat |  |  | assumed flat surfaces for all buildings
4b2 |  |  | Contour
4b3 |  |  | Rip
4b4 |  |  | Cover
4b5 |  |  | Growth Medium
Sloped
4b6 |  |  | Contour
4b7 |  |  | Rip
4b8 |  |  | Cover
4b9 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4b10 |  |  | Blade
4b11 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4b12 |  |  | Blade
4b13 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
4b14 |  | Clean-up Trash and Debris
Dismantling and equipment removal Subtotal
4c | Miscellaneous Sites - Millsite |  |  |  | from Miscellaneous Sites cost estimation worksheet (Millsite)
|  | Flat |  |  | flat = sloped production rate due to conveyor crossing, therefore all data input as flat
4c1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Miscellaneous Sites Reclamation increased by 50%
4c2 |  |  | Rip
4c3 |  |  | Cover
4c4 |  |  | Growth Medium
Sloped
4c5 |  |  | Contour
4c6 |  |  | Rip
4c7 |  |  | Cover
4c8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4c9 |  |  | Blade
4c10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4c11 |  |  | Blade
4c12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Miscellaneous Sites - Millsite Subtotal
4d | Miscellaneous Sites - Conveyor Crossing |  |  |  | from Miscellaneous Sites cost estimation worksheet (Conveyor)
|  | Flat |  |  | flat = sloped production rate due to conveyor crossing, therefore all data input as flat
4d1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Miscellaneous Sites Reclamation increased by 50%
4d2 |  |  | Rip
4d3 |  |  | Cover
4d4 |  |  | Growth Medium
Sloped
4d5 |  |  | Contour
4d6 |  |  | Rip
4d7 |  |  | Cover
4d8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4d9 |  |  | Blade
4d10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4d11 |  |  | Blade
4d12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Miscellaneous Sites - Conveyor Crossing Subtotal
4e | Miscellaneous Sites - Crusher Station |  |  |  | from Miscellaneous Sites cost estimation worksheet (Crusher Sta.)
|  | Flat |  |  | flat = sloped production rate due to conveyor crossing, therefore all data input as flat
4e1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Miscellaneous Sites Reclamation increased by 50%
4e2 |  |  | Rip
4e3 |  |  | Cover
4e4 |  |  | Growth Medium
Sloped
4e5 |  |  | Contour
4e6 |  |  | Rip
4e7 |  |  | Cover
4e8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4e9 |  |  | Blade
4e10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4e11 |  |  | Blade
4e12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Miscellaneous Sites - Crusher Station Subtotal
4f | Miscellaneous Sites - Pit Diversion Ditches |  |  |  | from Miscellaneous Sites cost estimation worksheet (Pit Diversion)
|  | Flat |  |  | flat = sloped production rate due to conveyor crossing, therefore all data input as flat
4f1 |  |  | Contour |  |  |  | 12' growth media to ensure adequate coverage; assume 1/2 contour cost for surface work and 1/2 for cover work therefore average unit cost for Miscellaneous Sites Reclamation increased by 50%
4f2 |  |  | Rip
4f3 |  |  | Cover
4f4 |  |  | Growth Medium
Sloped
4f5 |  |  | Contour
4f6 |  |  | Rip
4f7 |  |  | Cover
4f8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4f9 |  |  | Blade
4f10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces
Sloped
4f11 |  |  | Blade
4f12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Miscellaneous Sites - Pit Diversion Ditches Subtotal
4g | Miscellaneous Sites - Wetlands |  |  |  | from Miscellaneous Sites cost estimation worksheet (Wetlands)
|  | Flat |  |  | flat = sloped production rate due to conveyor crossing, therefore all data input as flat
4g1 |  |  | Contour |  |  |  | unit cost based on MDEQ estimation for flat surfaces, conservative estimate for wetlands reclamation
4g2 |  |  | Rip
4g3 |  |  | Cover
4g4 |  |  | Growth Medium
Sloped
4g5 |  |  | Contour
4g6 |  |  | Rip
4g7 |  |  | Cover
5g8 |  |  | Growth Medium
Earthwork/Recontouring Subtotal
Flat
4g9 |  |  | Blade
4g10 |  |  | Seeding (seed, equipment, labor) |  |  |  | unit cost based on MDEQ estimation for flat surfaces, conservative estimate for wetlands reclamation
Sloped
4g11 |  |  | Blade
4g12 |  |  | Seeding (seed + equipment + labor)
Revegetation/Stabilization Subtotal
Miscellaneous Sites - Wetlands Subtotal
4h | Install stormwater controls
Subtotal Facilities, Roads, Borrow Areas and Other
5 | Miscellaneous
5a | Detoxification/Disposal of Wastes
5b | Public Safety
Subtotal Miscellaneous
6 | Water Treatment Capture, Pump, Treatment and Discharge
6a | Interceptor wells
6b | Collection and distribution
6c | Degritting/equilization ponds
6d | Water treatment plant
6e | Sludge disposal facilities
6f | Effluent disposal facilities
Subtotal Water Treatment Capture, Pump, Treatment and Discharge
Total Tasks 1 thru 6
7 | Indirect Costs | [5 empty] | based on scenario 1 with 56% indirect costs | based on scenario 1 with 56% indirect costs | based on scenario 1 with 56% indirect costs
7a | Contingency |  |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
7b | Mobilization and demobilization |  |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
7c | Engineering redesign |  |  |  |  | 3% - allows for redesign of the existing reclamation plan to reflect current conditions in the event of bankruptcy
7d | Engineering, procurement, construction management |  |  |  |  | 5% - accounts for construction engineering and management on behalf of agency conducting reclamtion
7e | Contractor Overhead |  |  |  |  | 15% - covers administrative, management, safety, legal, and other costs
7f | Contractor Profit |  |  | 10% | from Summary Worksheet, 10% of contract cost | 10%
7g | Agency Administration |  |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
7h | Inflation |  |  | 8% | from Summary Worksheet, 8% of contract cost | 3%
Sub-Total Indirect Costs
Total Capital Cost
Total Cost |  |  |  |  | from subtotal capital costs plus subtotal operating consts | from subtotal capital costs plus subtotal operating consts | from subtotal capital costs plus subtotal operating consts | from subtotal capital costs plus subtotal operating consts | from subtotal capital costs plus subtotal operating consts
Note on K26: get reference!!!
Note on L26: get reference!!!

## Operating Cost Estimate
Detailed Reclamation and Closure/Closeout Bond Cost Estimate - Operating Costs
Fort Knox Mine Reclamation Plan
|  |  |  | Fort Knox Mine Reclamation Plan April 2001 | CSP2 2003 Estimate - Scenario 1 |  | CSP2 2003 Estimate - Scenario 2 |  | CSP2 2003 Estimate - Scenario 3 |  | CSP2 2003 Estimate - Scenario 4
Line |  | Tasks |  | Total Cost | Total Cost |  | Total Cost |  | Total Cost |  | Total Cost
1 | Interim Water Management and Operations |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Water Treatment Plant
2a | Labor
2b | Reagents
2c | Maintenance
2d | Analytical
2e | Electric Power
| Sub-Total Water Treatment Plant |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | General Site Operation and Maintenance
3a | Labor |  |  | 45696 |  | 45696 |  | 45696 |  | 45696 |  | 45696
3b | Maintenance
3c | Electric Power
3d | Office Expense
3e | Service Expense
3f | Site Security
| Sub-total General Site Operation and Maintenance |  |  | 45696 |  | 45696 |  | 45696 |  | 45696 |  | 45696
4 | Long-Term Operation and Maintenance Expense
4a | Surface and Groundwater Monitoring
4b | Reclamation Monitoring
4c | Reclamation Maintenance
4c1 |  | Manpower
4c2 |  | Equipment
4c3 |  | Materials and Supplies
| Sub-Total Long-Term Operation and Maintenance Expense |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Total Operating Costs |  |  | 45696 |  | 45696 |  | 45696 |  | 45696 |  | 45696
5 | Indirect Costs
5a | Contingency |  | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8
5b | Mobilization and demobilization |  | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8
5c | Engineering redesign |  |  |  | 3% | 1370.88 | 3% | 1370.88 | 3% | 1370.88 | 3% | 1370.88
5d | Engineering, procurement, construction management |  |  |  | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8
5e | Contractor Overhead |  |  |  | 15% | 6854.4 | 15% | 6854.4 | 15% | 6854.4 | 15% | 6854.4
5f | Contractor Profit |  | 10% | 4569.6 | 10% | 4569.6 | 10% | 4569.6 | 10% | 4569.6 | 10% | 4569.6
5g | Agency Administration |  | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8 | 5% | 2284.8
5h | Inflation |  | 8% | 3655.68 | 3% | 1370.88 | 3% | 1370.88 | 3% | 1370.88 | 3% | 1370.88
| Sub-Total Indirect Costs |  | 33% | 15079.68 | 51% | 23304.96 | 51% | 23304.96 | 51% | 23304.96 | 51% | 23304.96
6 | Water Treatment Plant Capital Replacement
10 yr @ 25% of Water Treatment Plant Capital Costs
20 yr @ 25% of Water Treatment Plant Capital Costs
40 yr @ 50% of Water Treatment Plant Capital Costs
10yr @ $2,000,000 for water management structures
Total Operating Cost |  |  |  | 60775.68 |  | 69000.96 |  | 69000.96 |  | 69000.96 |  | 69000.96
SUMMARY - Ft Knox Mine Tailings Storage Reclamation and Closure Estimate - Operating Costs (Indirect Costs Included)
Item1 | Interim Water Management and Operations |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Item 2 | Water Treatment Plant |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Item 3 | General Site Operation and Maintenance |  |  | 60775.68 |  | 69000.96 |  | 69000.96 |  | 69000.96 |  | 69000.96
Item 4 | Long-Term Operation and Maintenance Expense
|  | Surface and Groundwater Monitoring |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Reclamation Monitoring |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Reclamation Maintenance |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Sub-Total Long-Term Operation and Maintenance Expense |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Item 6 | Water Treatment Plant Capital Replacement |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Total Operating Reclamation Cost |  |  | 60775.68 |  | 69000.96 |  | 69000.96 |  | 69000.96 |  | 69000.96

## Operating Cost Assumptions
Detailed Reclamation and Closure/Closeout Bond Cost Estimate - Operating Costs
Fort Knox Mine Reclamation Plan
|  |  |  | Fort Knox Mine Reclamation Plan 2001 | CSP2 2003 Estimate - Scenario 1 | CSP2 2003 Estimate - Scenario 2 | CSP2 2003 Estimate - Scenario 3 | CSP2 2003 Estimate - Scenario 4
Line |  | Tasks
[5 empty] | duplicate Ft Knox Rec. Plan captial and operating costs, changes to indirect costs as noted | assess and change reclamation tasks and unit costs as noted, indirect costs from CSP2 scenario 1 | same assumpitons as CSP2 scenario 2 with 50 years water treatment | same assumpitons as CSP2 scenario 2 with 100 years water treatment
1 | Interim Water Management and Operations
2 | Water Treatment Plant
2a | Labor
2b | Reagents
2c | Maintenance
2d | Analytical
2e | Electric Power
Sub-Total Water Treatment Plant
3 | General Site Operation and Maintenance
3a | Labor |  |  | from Supervisor Labor column on cost estimation summary sheet
3b | Maintenance
3c | Electric Power
3d | Office Expense
3e | Service Expense
3f | Site Security
Sub-total General Site Operation and Maintenance
4 | Long-Term Operation and Maintenance Expense
4a | Surface and Groundwater Monitoring
4b | Reclamation Monitoring
4c | Reclamation Maintenance
4c1 |  | Manpower
4c2 |  | Equipment
4c3 |  | Materials and Supplies
Sub-Total Long-Term Operation and Maintenance Expense
5 | Indirect Costs |  |  |  |  | based on scenario 2 indirect costs | based on scenario 2 indirect costs | based on scenario 2 indirect costs
5a | Contingency |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
5b | Mobilization and demobilization |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
5c | Engineering redesign |  |  |  | 3% - allows for redesign of the existing reclamation plan to reflect current conditions in the event of bankruptcy
5d | Engineering, procurement, construction management |  |  |  | 5% - accounts for construction engineering and management on behalf of agency conducting reclamtion
5e | Contractor Overhead |  |  |  | 15% - covers administrative, management, safety, legal, and other costs
5f | Contractor Profit |  | 10% | from Summary Worksheet, 10% of contract cost | 10%
5g | Agency Administration |  | 5% | from Summary Worksheet, 5% of contract cost | 5%
5h | Inflation |  | 8% | from Summary Worksheet, 8% of contract cost | 3%
Sub-Total Indirect Costs
6 | Water Treatment Plant Capital Replacement
10 yr @ 25% of Water Treatment Plant Capital Costs
20 yr @ 25% of Water Treatment Plant Capital Costs
40 yr @ 50% of Water Treatment Plant Capital Costs
10yr @ $2,000,000 for water management structures
Total Operating Cost

## Cash Flow Estimates_Ft Knox
FORT KNOX MINE RECLAMATION PLAN 2001
PROJECT CASH FLOW
3 years
Year | Cost Area | [8 empty] | Total | Nominal Value | Present Value
| Capital Costs | [5 empty] | Operating Costs |  |  |  | Inflation = | Discount =
| Mine Waste Piles | Borrow Areas | Open Pit | Facilities, Roads and Other | Miscellaneous | Water Treatment | Water Treatment Plant O&M | General Site O&M | Long-Term O&M |  | 3% | 5%
0 | 329035.7933 | 171003.1889 | 9439.8967 | 172056.9928 |  |  |  | 20258.56 |  | 701794.4317 | 701794.4317 | 701794.4317
1 | 329035.7933 | 171003.1889 | 9439.8967 | 172056.9928 |  |  |  | 20258.56 |  | 701794.4317 | 722847.2647 | 687758.5431
2 | 329035.7933 | 171003.1889 | 9439.8967 | 172056.9928 |  |  |  | 20258.56 |  | 701794.4317 | 744532.7126 | 674003.3722
Grand Total | 987107.38 |  | 28319.69 | 516170.9784 | 0 | 0 | 0 | 60775.68 | 0 | 2105383.2952 | 2169174.4091 | 2063556.3471

## Cash Flow Estimates_Scenario 1
FORT KNOX MINE RECLAMATION PLAN - CSP2 SCENARIO 1
PROJECT CASH FLOW
3 years
Year | Cost Area | [8 empty] | Total | Nominal Value | Present Value
| Capital Costs | [5 empty] | Operating Costs |  |  |  | Inflation = | Discount =
| Mine Waste Piles | Borrow Areas | Open Pit | Facilities, Roads and Other | Miscellaneous | Water Treatment | Water Treatment Plant O&M | General Site O&M | Long-Term O&M |  | 3% | 5%
0 | 373566.9533 | 194146.4777 | 10717.4767 | 195342.9016 |  |  |  | 23000.32 |  | 796774.1293 | 796774.1293 | 796774.1293
1 | 373566.9533 | 194146.4777 | 10717.4767 | 195342.9016 |  |  |  | 23000.32 |  | 796774.1293 | 820676.3531 | 780838.6467
2 | 373566.9533 | 194146.4777 | 10717.4767 | 195342.9016 |  |  |  | 23000.32 |  | 796774.1293 | 845296.6737 | 765221.8737
Grand Total | 1120700.86 | 582439.433 | 32152.43 | 586028.7048 | 0 | 0 | 0 | 69000.96 | 0 | 2390322.3878 | 2462747.1562 | 2342834.6497

## Cash Flow_Scenario 2,3,4
FORT KNOX MINE RECLAMATION PLAN - CSP2 SCENARIO 2, 3, 4
PROJECT CASH FLOW
3 years
Year | Cost Area | [8 empty] | Total | Nominal Value | Present Value
| Capital Costs | [5 empty] | Operating Costs |  |  |  | Inflation = | Discount =
| Mine Waste Piles | Borrow Areas | Open Pit | Facilities, Roads and Other | Miscellaneous | Water Treatment | Water Treatment Plant O&M | General Site O&M | Long-Term O&M |  | 3% | 5%
0 | 845289.1917 | 549993.8846 | 34907.1733 | 954983.2121 |  |  |  | 23000.32 |  | 2408173.7817 | 2408173.7817 | 2408173.7817
1 | 845289.1917 | 549993.8846 | 34907.1733 | 954983.2121 |  |  |  | 23000.32 |  | 2408173.7817 | 2480417.9952 | 2360010.3061
2 | 845289.1917 | 549993.8846 | 34907.1733 | 954983.2121 |  |  |  | 23000.32 |  | 2408173.7817 | 2554830.565 | 2312810.1
Grand Total | 2535867.575 |  | 104721.52 | 2864949.6364 | 0 | 0 | 0 | 69000.96 | 0 | 7224521.3452 | 7443422.342 | 7080994.1878